## Slide 1
React UI Consolidation
Sprint-Based Roadmap | June 1 - October 1
4 Applications → Single React Platform | 9 Sprints (2-week cycles)
Product Manager: Shk | Team: 6 Members

## Slide 2
Sprint Roadmap: June 1 - October 1
Sprint 1
Jun 1-14
React Foundation Setup
CURRENT
Sprint 2
Jun 15-28
Password Reset Module
NEXT
Sprint 3
Jun 29-Jul 12
App A Core Workflows
PLANNED
Sprint 4
Jul 13-26
App B Core Workflows
PLANNED
Sprint 5
Jul 27-Aug 9
App C Core Workflows
PLANNED
Sprint 6
Aug 10-23
App D Core Workflows
PLANNED
Sprint 7
Aug 24-Sep 6
Cross-App Integration
PLANNED
Sprint 8
Sep 7-20
Alpha Testing & Fixes
PLANNED
Sprint 9
Sep 21-Oct 1
Beta Launch & Go Live
PLANNED

## Slide 3
SPRINT 1: React Foundation Setup (June 1-14)
Current Sprint | Delivery: Production-Ready React Shell with Auth
Deliverables:
✓ React + Redux architecture setup
✓ CI/CD pipeline configured
✓ Auth service layer (handles all 4 backends)
✓ Shared UI component library (Tailwind + Storybook)
✓ Unified navigation shell
Risks & Blockers:
🟡 DevOps CI/CD approval (Medium) → Using local setup, sync Wed
🟢 API contracts unclear (Low) → Direct eng access to backend teams
Status: ON TRACK
Confidence: 90% | Gate 1: June 21

## Slide 4
SPRINT 2: Password Reset Module (June 15-28)
Next Sprint | Delivery: Unified Password Reset Flow for All 4 Backends
Deliverables:
✓ Password reset form (unified UI)
✓ Backend adapter for all 4 auth systems
✓ Email notification service
✓ Error handling & validation
✓ QA testing (all 4 backends)
Risks & Blockers:
🟡 App B email service format (Medium) → Adapter workaround ready
🟡 App D auth token lifespan (Medium) → Need backend clarification by Mon
Dependencies: Sprint 1 complete, backend API clarity

## Slide 5
SPRINTS 3-6: Core Workflows by App
Sprint 3 | App A | Jun 29-Jul 12
Features: Create, View, Edit, Delete, Dashboard
Risk: High complexity
Sprint 4 | App B | Jul 13-26
Features: Search, Filter, Export, Dashboard
Risk: API rate limiting
Sprint 5 | App C | Jul 27-Aug 9
Features: Approve, Reject, Reports, Dashboard
Risk: Report formatting
Sprint 6 | App D | Aug 10-23
Features: Monitor, Config, Alerts, Dashboard
Risk: Real-time sync

## Slide 6
SPRINTS 7-9: Integration, Testing, Launch
Sprint 7 | Cross-App Integration (Aug 24-Sep 6)
Data flow between apps, performance opt.
Sprint 8 | Alpha Testing & QA (Sep 7-20)
Defect fixing, load testing, security review
Sprint 9 | Beta & Production Launch (Sep 21-Oct 1)
Beta user feedback, final fixes, go live

## Slide 7
Questions for Architect (Pre-Sprint 1)
1. API Versioning: How do we handle breaking changes if backends update during sprints?
2. Auth Token Management: Refresh token lifecycle? Same token for all 4 backends or separate?
3. Data Sync: Which app is source-of-truth if user data conflicts across backends?
4. Performance: Caching strategy? Should we batch API calls or call per-action?
5. Error Handling: How granular? Same error message for all 4 apps or backend-specific?
6. Testing: Mock backends or real? How do we isolate 4 APIs during QA?
7. Logging: Centralized logging across 4 backends? How to trace issues?
8. Rollback: If App D deploy fails, can we deploy other 3 apps independently?

## Slide 8
Sprint Success Criteria (All Sprints)
Definition of Done (Every Sprint):
✓ Code reviewed + merged to main
✓ Unit tests + integration tests pass
✓ QA sign-off (no critical defects)
✓ Performance acceptable (<2s load time)
✓ Security review passed
✓ Documentation updated

## Slide 9
Risk Register: Critical Risks Across Sprints
Backend API instability
1-9
Mock APIs in staging
MEDIUM
Data migration issues
3-6
Early data audit (Sprint 1)
HIGH
Performance degrades with 4 APIs
5-7
Load test in Sprint 6
MEDIUM
Scope creep from stakeholders
1-9
Lock scope by Sprint 1 gate
HIGH
Team member leaves
1-9
Knowledge sharing, pair programming
LOW

## Slide 10
External Dependencies & Blockers
Backend Teams
1-9
API contracts, stability, docs
Your manager to escalate
DevOps
1
CI/CD pipeline approval
Direct sync (Weekly)
Beta Users
8
50 power users for testing
HR/Management
Security Team
7-8
Security review + compliance
Your manager