## Slide 1: Go-Live in March through canary rollout; Core API, Data Sync and Claude Code set the pace
MYIAM ROADMAP · EXECUTIVE VIEW
Critical path
Build
Oct–Dec '26
M1
UX prototype delivered
End Oct · in progress
M2
Data Sync delivered
Mid Nov
M3
Core API delivered
Mid Dec
Validate
Jan '27
M4
Integration & testing
Mid Jan
M5
DST approved
Mid Jan
M6
UAT sign-off
End Jan
Release
Feb–Apr '27
M7
Beta release
End Feb · canary 1% → 10%
M8
Go-Live
End Mar · canary ramp
M9
Access live
Apr · Access Control
CRITICAL PATH
Data Sync, Core API / AD Write and Claude Code availability gate every release. If one slips, Beta, Go-Live and Access all move.
NEEDS FROM LEADERSHIP
Confirm Claude Code licences for the pilot team
Protect Core API / AD Write capacity through mid Dec
Hold DST and UAT review slots in January
MyIAM · Executive roadmap · Oct 2026
All dates are completion dates · Go-Live rolls out by module in canary mode
Notes: Message: Go-Live is March, delivered in canary mode by module, with Access following in April. Three enablers decide the date: Data Sync (mid Nov), Core API / AD Write (mid Dec) and Claude Code availability. If any one slips, Beta, Go-Live and Access all move. Beta means the internal 1% and pilot 10% canary stages; Go-Live is the ramp to all users. Asks: Claude Code licences confirmed for the pilot team, Core API / AD Write capacity protected through mid December, and DST and UAT review slots held in January.

## Slide 2: Enablers done by mid Dec; Go-Live end Mar, Access Apr
MYIAM ROADMAP · TIMELINE
Critical path
WORKSTREAM
Oct '26
Nov
Dec
Jan '27
Feb
Mar
Apr
May
Jun
MILESTONES
ENABLERS
VALIDATE
RELEASE
CLOSE-OUT
Marker = module go-live
Today
Beta · End Feb
Go-Live · End Mar
Core API gate
Zero buffer: each week Core API slips moves Go-Live by a week
UX prototype
Data Sync
Claude Code available
Core API / AD Write
Integration & testing
DST approved
UAT sign-off
Password + Solutions
Accounts
Access Control
incl. Groups
Hypercare
Legacy exit
Communications
End Oct
Mid Nov
End Oct
Mid Dec
Mid Jan
Mid Jan
End Jan
End Mar
Apr
Apr
May
Jun
Pre-release
Release
Closure + survey
Markers show completion dates only · MyAppConnect is out of scope
Canary detail: next slide
Notes: Completion dates only; no start dates. The amber path is the critical path: Data Sync (mid Nov) and Claude Code availability (end Oct) both feed Core API / AD Write (mid Dec), which feeds Integration and testing in mid Jan, then DST approval and UAT sign-off at the end of January, then the first go-live. Beta is end Feb and Go-Live is end Mar, shown as dashed guide lines. Password and Solutions go live at the end of March; Accounts and Access Control, which includes Groups, follow in April. Hypercare completes in May and legacy exit in June. The shaded zone to the right of the Core API gate is everything that depends on it. There is no buffer: each week Core API slips moves Beta, Go-Live and Access by a week. How the canary rollout works is on the next slide.

## Slide 3: Go-Live is a gated canary, released module by module
MYIAM ROADMAP · HOW GO-LIVE HAPPENS
STAGES
Every step needs a clean time window and a manual sign-off
UAT
Formal testing and business sign-off
Internal · 1%
Beta-internal cohort
Pilot · 10%
Beta-pilot cohort
Live
Ramp to all users = Go-Live
RELEASE ORDER
MyAppConnect is out of scope
1
Password
2
Solutions
3
Groups
4
Accounts
5
Access Control
PREREQUISITES
AD Write consolidation and AD → DB Data Sync must both complete before any module canary starts.
ONE MODULE AT A TIME
Each module has its own cohort. The next module starts once the previous one clears its pilot gate.
SAFETY NETS
Access Control needs at least 3 weeks from pilot to ramp. A failed pilot means fall back, replan, redeliver.
Module status: Not released → UAT → Internal → Pilot → Live
Dates: previous slide
Notes: Go-Live is not a single cutover. Each module moves through UAT, then an internal 1% cohort, then a 10% pilot, then a ramp to all users. The canary is the beta: internal is beta-internal and pilot is beta-pilot. Every step needs both a clean time window and a manual sign-off. Prerequisite: AD Write consolidation and the AD to DB Data Sync both complete before any module canary starts. Release order is Password, Solutions, Groups, Accounts and Access Control; the next module starts once the previous one clears its pilot gate. Access Control has a hard minimum of 3 weeks from pilot to ramp, and the April date may flex rather than compress that window. If a pilot does not succeed, the team falls back, replans and delivers again. MyAppConnect is out of scope.