## Slide 1
ROADMAP
MyIAM · Canary Release Plan – Module Rollout
Prerequisite: AD Write Consolidation + AD→DB Data Sync complete – every module tested end-to-end · canary window = 2.5wk (Internal 1wk + Pilot 1.5wk)
Jan '27
Feb '27
Mar '27
Apr '27
May '27
1. Password Reset
Runs in parallel with Solution → retires MyPassword
Internal 1%
Pilot 10% → Ramp 25/50/75/100%
◇ Pilot clear
✓ 100% – 7wk mark
2. Solution (Solutions + Context)
Runs in parallel with Password Reset → no legacy app to retire
Internal 1%
Pilot 10% → Ramp 25/50/75/100%
◇ Pilot clear → starts Accounts
✓ 100% – 7wk mark
3. Accounts
Starts once Solution clears its pilot gate → retires MyAccount
Internal 1%
Pilot 10% → Ramp 25/50/75/100%
◇ Pilot clear → starts Groups
✓ 100% – 9wk mark
4. Groups
No legacy app to retire
Internal 1%
Pilot 10% → Ramp 25/50/75/100%
◇ Pilot clear → starts Access
✓ 100% – 12wk mark
5. Access
Depends on validated Groups data → hard floor: 3wk pilot-to-ramp → retires MyAccess
Internal 1%
Pilot 10% → Ramp 25/50/75/100%
◇ Pilot clear
✓ 100% – 14wk mark
⚑ Prerequisite complete
Internal 1% (dark)
Pilot 10% → Ramp (light)
Pilot gate clear (triggers next module)
100% – module live
⚠ Password Reset and Solution start together in week 1 of January 2027 and run in parallel. Every gate requires a clean window (4 business days minimum) AND manual sign-off — Programme Lead also signs off before every module's Ramp. Access carries a hard floor of 3 weeks pilot-to-ramp. Chain completes around wk14 (~mid-Apr 2027), close to the original production date.