## Slide 1
4
AIRBUS · IAM CONVERGENCE PROGRAMME
MyIAM
Parallel Delivery Model — Revised Plan
May 2026 – Apr 2028 · 4 Concurrent Workstreams
4
Workstreams
running in parallel
0
Sequential
phase gates
130K+
Airbus users
targeted
1
Unified platform
end state
Airbus Commercial · IIDIA · Internal – v1.0 · Sep 2026

## Slide 2
STRATEGIC VIEW
MyIAM Runs as Four Concurrent Workstreams
No workstream waits for another to finish. Delivery risk is continuous, not concentrated at a single cutover.
UI
UI Consolidation
UX: 5/6 DONE
UX complete for Solutions, Identity, Context, Groups, Password. MyAppConnect UX not started.
MyAppConnect is the one gap
API
API Development
API: 5/6 DONE
Python APIs live for Solutions, Context, Groups, Password, Identity. Accounts has no API yet.
Accounts is the one gap
DS
Data Sync (Prefect)
IN PROGRESS
Prefect hosting complete; now integrating additional data sources beyond AD into the shared DB.
Prefect, not Apache NiFi
AD
AD Write Consolidation
NOT STARTED
No authorised write path to AD yet. Read-only today — this is the critical path.
Single write path to AD — pending
Key shift from the phased Roadmap v3: AD Write Consolidation is not gated behind the other three — it runs alongside them and is now the single workstream that determines overall programme completion.
AIRBUS · IAM Convergence Programme
Strategic Workstream View
2

## Slide 3
ROADMAP
MyIAM · Beta Feb 2027 → Production Apr 2027 → Access Entitlement
2026
2027
2028
Q2 2026
May–Jul
Q3 2026
Aug–Oct
Q4 2026
Nov–Jan
Q1 2027
Feb–Apr
Q2 2027
May–Jul
Q3 2027
Aug–Oct
Q4 2027
Nov–Jan
Q1 2028
Feb–Apr
BETA → PRODUCTION
Foundation
& Build
Data &
Integration
Identity
Core
Access &
Entitlement
UI Consolidation
MFE shell · 5 of 6 assets’ UX done · MyAppConnect pending
MyAccess UI · 5 Assets Live · MyAppConnect Pending
5 of 6 live
UX Design
Hardening
✓ Beta Ready
API Development
Python APIs · 5 of 6 assets built · Accounts pending
Domain APIs · Solutions + Context + Groups + Password + Identity
Accounts pending
API Build
Hardening
✓ Beta Ready
Data Sync (Prefect)
Config-over-code · Multi-source integration
Prefect Pipelines · AD → MyIAM DB · Multi-Source Sync
Hosting complete
Pipeline Build
✓ Sync Live
AD Write Consolidation
Sole write authority · Dual-write / rollback safety
○ PROTOTYPE
AD Write Arch
Core API · Domain Write Ops · AD Write Authority
Single write path live
Design
Build Write Path
✓ Live (G2)
Access Entitlement Mgmt
Discovery first — workflow unproven · catalog + fulfillment via AD write (G2)
Discovery, Brainstorming & Requirements Gathering
○ PROTOTYPE
Catalog Design
Access Packages · Catalog & Approval · Auto-Fulfillment
G5 Live
Discovery & Workshops
✓ Entitlement Model & Workflow Spec
Catalog Design
Workflow Build
✓ Entitlement Live
G6 — Persona-Aware Access →
Abhishek Reddy · Programme Lead
Go-live
Decision
Decision Gate · Sign-off required
AIRBUS · IAM Convergence Programme
Roadmap
3

## Slide 4
PROGRAMME STATUS
Where MyIAM Actually Stands Today
Verified status as of September 2026, asset by asset — replaces the Roadmap v3 phase-exit assumptions.
✓
UX Design
5 / 6 ASSETS
Solutions, Identity, Context, Groups, Password done. MyAppConnect UX not started — carries connector + scope management complexity.
✓
API Layer
5 / 6 ASSETS
Python APIs live for Solutions, Context, Groups, Password, Identity. Accounts has no API or schema yet.
~
Schema / LPA
5 / 6 ASSETS
LPA-designed schema built from scratch for the same 5 assets. Accounts is the one gap — and it underpins AD write design.
✓
Data Pipeline
OPERATIONAL
Prefect hosting complete; now integrating additional data sources beyond AD into the shared DB.
!
AD Write Path
NOT STARTED
All AD access today is read-only. No authorised single write path exists yet — the critical path to completion.
Also true today: MyIAM is hosted in lower environment only — nothing above is at production scale yet. CI/CD pipelines for both API and UI are complete, which de-risks the eventual prod promotion and the Accounts/MyAppConnect build-out still ahead.
AIRBUS · IAM Convergence Programme
Current Status Snapshot
4

## Slide 5
DELIVERY PHILOSOPHY
Configuration-over-Code, Across UI, API & Data Sync
The same engineering choice, made independently in three places: build one engine, drive behaviour from configuration rather than per-asset code.
UI
One metadata-driven UI engine renders list/detail screens per asset from config — not one hand-built screen per asset.
API
Python API layer is config-driven, not hard-coded per asset — new fields/rules ship as config changes.
Data Sync
Prefect flows are configuration-over-code by design — pipelines defined declaratively, not scripted per source.
PROS
One engine to build/test/secure instead of six-plus per-asset implementations — Accounts and MyAppConnect inherit it once built, rather than starting from zero.
Consistency by construction: every asset gets the same LPA, audit, and validation behaviour automatically — no per-asset drift.
Faster iteration once the engine is stable — new fields or asset variants ship as config, not a code + redeploy cycle.
Lower long-term maintenance surface: one codebase to patch and review, not N near-duplicate ones.
CONS
Debugging is harder — failures surface inside the config-interpretation layer, one step removed from a stack trace tied to a specific asset.
Edge cases strain the model: unusual approval workflows (e.g. MyAppConnect's cross-context scope approval) may not fit generic config cleanly.
Governance risk is real for IAM specifically: config changes need the same review/audit rigour as code changes, or they become an ungoverned back door.
Concentrates critical knowledge in whoever built the engine — reinforces the single-point-of-failure capacity risk already on the register (R6).
AIRBUS · IAM Convergence Programme
Configuration-over-Code
5

## Slide 6
PROGRAMME RISK REGISTER
Delivery Risks & Mitigations
7 risks tracked · 1 carried unmitigated · 1 new critical risk (AD write path)
R1
IMPORTANT
MyAccess UI Consolidation
Cause
3-app merge (MyAccount, MyPassword, MyAppConnect) carries real refactor complexity.
Mitigation
Technical consolidation first; full UX redesign deferred to a later iteration.
R9
CRITICAL · NEW
AD Write Path Not Yet Built
Cause
No authorised write path to AD exists. This is now the single gate the whole programme depends on.
Mitigation
Design dual-write/rollback safety before any write capability ships; treat as top priority.
R3
IMPORTANT
Feature Freeze Boundary
Cause
Post-freeze feature additions create scope gaps against the locked baseline.
Mitigation
PM owns freeze sign-off with each product team; scheduled re-adjustment sprints.
R10
IMPORTANT · NEW
Schema Fragmentation
Cause
Shared database, but schema still separate per source — not yet unified.
Mitigation
Track schema unification as an explicit backlog item toward G3, not an assumed byproduct.
AIRBUS · IAM Convergence Programme
Risk Register · Delivery
6

## Slide 7
PROGRAMME RISK REGISTER
Constraints & External Dependencies
Internal Constraint — accepted, no mitigation
External Dependency — requires executive commitment
R6
CRITICAL · CONSTRAINT
Resource Availability — Team Capacity
Ongoing throughout all four workstreams · May 2026 – Apr 2028
Cause: Team is at capacity across UI, API, Data Sync and AD Write workstreams running concurrently, plus live support. Contractor availability not guaranteed. Key architects are single points of failure.
Status: NO MITIGATION PLANNED — ACCEPTED CONSTRAINT. If capacity is exceeded, escalate to reprioritisation, not schedule compression across workstreams.
R7
CRITICAL · DEPENDENCY
AD/LDAP Team Support — Now the Critical Path
Immediate · required to start AD Write Consolidation workstream
Cause: AD Write Consolidation cannot begin design in earnest without a dedicated AD/LDAP liaison. Since this workstream is no longer gated behind others, delay here delays the whole programme's end date, not just one phase.
Status: NO MITIGATION POSSIBLE — EXTERNAL DEPENDENCY. Requires: dedicated AD liaison assigned now; joint working session with AD lead; escalation to Abhishek Reddy if capacity is withdrawn.
AIRBUS · IAM Convergence Programme
Risk Register · Constraints
7

## Slide 8
LONG-TERM VISION
Beyond G4 — Abstracting IAM Away From the User
Two further gates, sequenced deliberately after the plumbing (G2 AD write, G3 schema) is trustworthy.
G5
Access Package Management
Entitlement Management
Business-meaningful bundles (“GIS Engineer — PLMDoc Contributor”) replace raw Groups/Scopes/Contexts as the unit end users request. One line, tied to employee ID.
CAN START NOW
Catalog + request/approval workflow
GATED ON G2
Automatic fulfillment
G6
Persona-Aware Intelligent Access
Conversational / Agentic Layer
Natural-language interface per persona — end users, architects, IAM admins — built on the existing agentic assistant work (LangGraph, RAG, tool-calling).
CAN START NOW
Design & prototyping
GATED ON G2 + G3 + G5
Acting on the user's behalf
Sequencing: G3 (Schema Unified) → G5 catalog & workflow (parallel-buildable now) → G2 unlocks G5 fulfillment → G6 agent layer builds on a mature G5.
AIRBUS · IAM Convergence Programme
Long-Term Vision
8

## Slide 9
G5 WORKED EXAMPLE
One Request, Six Assets Provisioned Behind It
Requester sees: “GIS Engineer — PLMDoc Contributor” — view & upload GIS project documents in PLMDoc.
Bundled Behind the Scenes
Account
Third-Party (TA), tied to employee ID, end-dated to contract
Password
Issued via self-service activation on first login
Groups
GRP_STC_EU_1Z60-LICENSEE-...-GIS-UEA
Context
CX_APP_EU_1Z60_1Z60
Scopes
PUBLI_READ, PUBLI_CREATE, DMS_READ
Connector
OIDC grant activating login to PLMDoc
The Workflow
1
Request
Requester searches the catalog by role/task, not by scope code.
2
Approval
Package owner approves; sensitive packages can require two-step sign-off.
3
Fulfillment
Account → Group → Context/Scope → Connector, provisioned in dependency order.
4
Notification
“You now have PLMDoc Contributor access” — no group/scope jargon.
5
Recertification
Contractor packages auto-expire at contract end; others recertify periodically.
Governance note: Packages that make access easy to get must also make it easy to revoke — recertification is not optional, it's what keeps this from becoming an audit finding.
AIRBUS · IAM Convergence Programme
G5 Worked Example
9

## Slide 10
CALL FOR ACTION
Capacity Escalation Path
The team is at capacity across all four concurrent workstreams. No mitigation exists today — if delivery is squeezed further, we need PM & HO backing to prioritise scope, not compress workstreams against each other.
ASK: Approve an escalation path: capacity issues go to reprioritisation, not timeline compression.
AD/LDAP Team Commitment — Now Urgent
AD Write Consolidation is the workstream every other gate ultimately depends on, and it hasn't started. This is an external dependency we cannot mitigate alone — it needs executive commitment now, not after Gate 3.
ASK: Confirm a dedicated AD liaison for MyIAM immediately, with an early joint working session.
Also flagged for awareness: Mobile Platform + Passport Decommission scope remains pending and is not yet on a workstream — a decision is needed once AD Write Consolidation reaches design maturity.
AIRBUS · IAM Convergence Programme
Call for Action
10

## Slide 11
4
AIRBUS · IAM CONVERGENCE PROGRAMME
Thank you!
MyIAM · 4 Workstreams · 1 Platform
AIRBUS · IAM Convergence Programme
Thank you
11