## Slide 1
4
AIRBUS · IAM Convergence PROGRAMME
MyIAM
Foundational Journey - Draft 2
June 2026 – Apr 2028 · 4 Phases
4→1
IAM Self service tools
1 Url
One experience for ~100k Users
100%
Modernized
Airbus Commercial · IIDIA
Mobile App
iOS+Android MyIAM App

## Slide 2
STRATEGIC PHASE VIEW
MyIAM Foundational Journey
May 2026 → Apr 2028
Phase 1 · MFE Consolidation
Phase 2 · Core Backend & Integration
Phase 3 · Domain APIs + Zero Trust
Phase 4 · Mobile Platform + Passport Decom
SCOPE TBD
May 2026
Nov 2026
May 2027
Nov 2027
Apr 2028
01
MFE CONSOLIDATION
Unified Cockpit Live March 2027
Release 1: MyAccess UI Convergence (technical merge)
· Release 2: MFE Shell (refined UX) · April 2028
KEY METRICS
- One identity experience for 100K+ Airbus users
- 4 applications converged into 1 unified platform
- ≥80% user adoption at Gate 1
PROGRAMME DELIVERS
MFE Shell · Kendo · 4 MFE Modules · Legacy UIs Retired
⬥ G1: Unified cockpit live · 100K+ users onboarded · Adoption ≥80%
02
CORE BACKEND & INTEGRATION
Secure Foundation Live
Secure data foundation - one pipeline in, one authorised write path out
KEY METRICS
- Single authorised write path to Active Directory
- All IAM sources unified into one secure data layer
- Full auditability enforced from day one · Zero data loss validated
PROGRAMME DELIVERS
Apache NiFi · MyX DB Cluster · Core API · Schema Unification
⬥ G2: Secure foundation live · Single write path validated · Zero data loss confirmed
03
DOMAIN APIS + ZERO TRUST
Platform Backbone Live
Platform backbone live - scalable, resilient, Zero Trust enforced
KEY METRICS
- Legacy systems fully marked for decommissioned ·
- Security posture elevated , Zero Trust enforced across all IAM self ser operations
PROGRAMME DELIVERS
API Gateway · 4 Module APIs · Business Logic Migrated · APIs marked for retirement
⬥ G3: Platform backbone live · Ready for Legacy decommissioned · Zero Trust enforced
04
MOBILE PLATFORM + PASSPORT DECOM
MyIAM Mobile Platform
One MyIAM platform across all channels · Web · Mobile · Airbus Passport decommissioned
KEY METRICS
- MyIAM accessible on iOS and Android , full self-service on mobile
- Airbus Passport functionality absorbed into MyIAM cockpit
- Airbus Passport formally marked for decommission at Gate 4
PROGRAMME DELIVERS
iOS + Android - MyIAM Mob EIS · Airbus Passport Decom starts
⬥ G4: MyIAM Mobile live · Airbus Passport marked for decom
⬥ Out of scope -1. IAM Copilot 2. Decommission of MyX Applications planning
- Resilient microservice architecture , no single point of failure
SCOPE TBD
Pending G4

## Slide 3
2026
2027
2028
Q2 2026
May–Jul
Q3 2026
Aug–Oct
Q4 2026
Nov–Jan
Q1 2027
Feb–Apr
Q2 2027
May–Jul
Q3 2027
Aug–Oct
Q4 2027
Nov–Jan
Q1 2028
Feb–Apr
MyAccess UI Convergence · 3 Apps Absorbed (MyAccount, MyPassword, MyAppConnect)
from 4 to
1 app
Beta Release
Data Tier · Source X → MyIAM DB Sync · (Apache nifi + Micro db)
NiFi Pipelines
AD→MyX Sync
Schema
Validation
✓ Foundation R2
Core API · Domain Write Operations · AD Write Authority
⬡ Proto: Arch
+Interface
Domain
Write Ops
✓ Core API
Live R3
G2
API microservice· 4 Domain APIs · Legacy APIs Retired
5 APIs →
1 Gateway
API Gateway
Design
Password +
Account APIs
Group +
SSO APIs
✓ Legacy
Retired R4
No Direct AD Access · PAP Policies · JIT Privileged Access
100%
time-bound
PAP Policy
Design
JIT Access
Live
✓ Zero
Direct AD
iOS+Android · Airbus Passport Decom · Platform Hardening
iOS+Android
ARD Review
Mobile Beta
Copilot
✓ Mobile Live
Live
G4
MFE
Consolidation
Core Backend
& Integration
Module APIs
+ Zero Trust
Mobile Platform
+ Passport Decom
MFE Consolidation
MFE Shell · Angular ModFed · OAuth2 · 4 Modules · ⬡ NiFi / Core API / Domain API Prototypes run in parallel during Phase 1
NiFi Pipelines
& MyX DB Cluster
Apache NiFi · AD→MyIAM DB · Schema Unification
Core API
Sole Write to any data source· Audit + Security
Module APIs
+ Zero Trust
4 MyX APIs marked for Retirement
Zero Trust & JIT
No Direct AD · PAP Policies · JIT Access
Mobile Platform + Passport Decom
iOS+Android · Airbus Passport Decom · Platform Hardening
MyIAM
Roadmap · May 2026 → Apr 2028
Go-live : 4 release
Decision
G1–G4 Decision gate · Abhishek Reddy sign-off required
⬡ PROTOTYPE
NiFi Design
⬡ PROTOTYPE
Core API Arch
⬡ PROTOTYPE · Domain API Gateway Design
⬡ PROTOTYPE
MFE Design
Mobile Platform
+ Passport Decom
SCOPE TBD · To be decided after G3 · HO approval required
✓ Cockpit Live - R1
Initial design: API microservice
Initial design: Core API
MFE Shell · Angular ModFed · Micro-Frontend Modules
✓ MFE R5

## Slide 4
PROGRAMME RISK REGISTER
Dependency Risks & Mitigations
6 risks · 1 not mitigated
R5
CRITICAL ★ NEW
Phase 2 API modernization breaks Phase 1 MFE modules
Phase 1 go-live (Oct 2026) → Phase 2 transition (Nov 2026)
Cause:
Phase 1 ships MFE to 200K+ users on legacy APIs. Phase 2 replaces them with domain APIs — different contracts. Modules break without refactoring.
Mitigation:
API Gateway backward compatibility layer. 2–4 week parallel operation window. Coordinate API contracts Q2 2026. Module refactoring in Phase 2 early weeks.
Mitigations additive to existing roadmap
R1
IMPORTANT ★
R1 – Phase 1: MyAccess UI Consolidation (3-app merge technical complexity)
Q2 2026 module development → potential Q3 delays
Cause:
MyAccess consolidation of 3 apps requires significant technical refactoring. Minimal UX experience . UI development rework
Mitigation:
Phase 1 (May-Jan 2026): Focus on technical consolidation only. Defer full redesign to Phase 2. Early design sprints (Apr-Jan 2026) define integration patterns and full redevelopment for better UX and adaptation. New features cant be accommodate until Release 5
R2
CRITICAL ★
Legacy API contracts not optimized for MFE consumption
Phase 1 go-live (Jan 2026) and Phase 2 transition (Apr 2027)
Cause:
Legacy MyX APIs return monolithic payloads. MFE modules can't fetch independently — causes full-payload overhead and breaking changes when Phase 2 APIs replace them.
Mitigation:
Phase 1: API adapter layer + shared state mgmt. Phase 2: Granular domain APIs per module. 4-week API coexistence window. Refactoring sprints in Phase 2 weeks 2–4.
R4
CRITICAL ★
Data Sync(Nifi) & Core Engine
Architecture review — hits Q3/Q4 2026
Cause:
Both POCs should succeed with target metrics for exit criteria
Mitigation:
None
R3
IMPORTANT
Feature Freeze — Post-May 2026 changes create scope gaps
Locked March 2026 · Delta review at each G1–G4 gate
Cause:
Features frozen at March 2026 baseline. Post-freeze additions create gaps in MFE module scope.
Mitigation:
PM owns feature freeze sign-off with each product team. Re-adjustment sprints at end of Phase 1 & 3.
R6
IMPORTANT
Infrastructure dependency
Locked March 2026 · Delta review at each G1–G4 gate
Cause:
Mitigation:

## Slide 5
PROGRAMME RISK REGISTER
Constraints & External Dependencies
🟣 R6 Internal Constraint: team at capacity ceiling; accepted; 🔵 R7 External Dependency - AD team support required
R6
CRITICAL ★ CONSTRAINT
Resource availability — Team capacity
Ongoing throughout Phases 1–4 · May 2026 – Apr 2028
Cause:
Team at capacity ceiling across Phase 1 (MFE), Phase 2 (API), Phase 3 (core backend ) and live support in parallel. Contractor availability not guaranteed. Key architects are single points of failure — no redundancy.
Status:
NO MITIGATION PLANNED — ACCEPTED CONSTRAINT. Programme gates (G1–G4) absorb schedule pressure without compressing scope. If capacity is exceeded → escalate to Product manager and reprioritization, not roadmap compression.
R7
CRITICAL ★ DEPENDENCY
AD/LDAP team continuous support required for foundation (Phases 1 & 2)
Ongoing Q2 2026 – Q2 2027 · Phases 1–2 critical path
Cause:
Base foundation metrics are decided based on AD integration. We need advice and continuous support to set a solid foundation with respect to Data Sync and Core API
Status:
NO MITIGATION POSSIBLE - EXTERNAL DEPENDENCY. Requires executive commitment before Gate 0: · Dedicated AD team liaison assigned to MyIAM for Phases 1 & 2 · Joint meeting (MyIAM PM + AD Lead) to surface conflicts early · Escalation: Abhishek Reddy - if AD capacity withdrawn, gate pauses

## Slide 6
RESOURCE & CAPACITY · IAM Convergence PROGRAMME
Resource Management
SP = Story Points · 40 SP velocity · 2-week sprints · Mobile: 8 SP / dedicated dev
40 SP
Velocity per sprint
2-week cadence
403 SP
Total programme scope
403 SP total programme scope
9
Sprints to deliver
18 weeks execution
STORY POINT DISTRIBUTION PER PHASE
Phase 1
MFE Consolidation
99 SP
3 sprints
Phase 2
Core Backend & Integration
168 SP
5 sprints
Phase 3
Domain APIs + Zero Trust
123 SP
3 sprints
Phase 4
Mobile Platform + Passport Decom
13 SP
1 sprint
SPRINT PLAN AT 40 SP VELOCITY
Sprint
Ph
Work Items
Story Points
S1
P1
Shell + MFE
Initial Build (5)
29
S2
P1
Pwd and Account module
Module 1 & 2
40
S3
P1
Access and SSO module
Module 3 & 4
40
S3
P2
NiFi Design + Schema (21)
Database cluster setup
40
S4
P2
Core API Arch (14)
Data Sync
40
S5
P2
Core API Writes (21)
AD write operations
40
S6
P2
Schema Validation (21)
Integration 1
40
S7
P3
API Gateway (21)
Integration 2
40
S8
P3/4
Mobile Beta + iOS (26)
40
8 SP
Mobile Track
iOS + Android · 1 Sprint
⚠ RISK: 40 SP velocity per sprint is a critical assumption. Any velocity drop below 40 SP will extend programme timeline.

## Slide 7
4
AIRBUS · IAM Convergence PROGRAMME
Thank you!
Airbus Commercial · IIDIA