## Slide 1
AIRBUS · Converged IAM Programme
Airbus Amber
MyIAM
One Self-Service Cockpit
Foundational Journey · May 2026 – Apr 2028 · 4 Phases
4→1
IAM self-service tools
1 URL
One experience · ~100k users
100%
Modernized
4 Apps
Legacy MyX apps retired
DRAFT

## Slide 2
Strategic
Phase
View
MyIAM Foundational Journey
· May 2026 → Apr 2028
01
PHASE 1 · UI Consolidation
Unified Cockpit Live · Mar 2027
• Release 1: MyAccess UI convergence (technical merge)
• Release 2: MFE Shell - refined UX · Apr 2028
PROGRAMME DELIVERS
MFE Shell · Kendo Framework · 4 MFE modules · legacy UIs retired
⬥ D1 & D4 · Unified cockpit live · 100K+ users onboarded
02
PHASE 2 · Core Backend & Integration
⬥ D2 · Secure foundation live · faster sync & write
03
PHASE 3 · Module APIs + Secure by Design
⬥ D3 · Backbone live
· Ready for MyX Apps decommission
04
PHASE 4 · Decommissioning
⬥ D4 · MyX apps decommissioned · 4 apps retired
Airbus Amber
3
Vision: Establish MyIAM as the unified entry point and definitive source of truth, effectively eliminating the need for direct Active Directory (AD) access.
Converged IAM Scope
PSL Vision on Self Service
Secure Foundation Live
• One pipeline in, one authorised write path out
• Full data sync with auditability from day one
CONVERGED IAM SCOPE
PSL VISION ON SELF SERVICE
PSL VISION ON SELF SERVICE
PSL VISION ON SELF SERVICE
PROGRAMME DELIVERS
MyIAM DB Cluster · Apache NiFi (data read)· Core API (data write)
Platform Backbone Live
• Scalable, resilient, Zero Trust enforced microservice
• Legacy systems fully marked for decommission
PROGRAMME DELIVERS
API microservice
· 4 Module APIs + CIGA API’s revamp · logic migrated
MyX Apps Sunset
• MyX apps retired as MyIAM becomes platform of record
• Annual upgrade cadence from 2029 (Jul–Aug)
PROGRAMME DELIVERS
MyX Apps sunset · 4 apps retired · decom complete
DRAFT

## Slide 3
Out of
Scope
Descoped & deferred items
· Reassessed for future phases
.Coding assistant Claude Code availability
MyIAM Mobile Platform + Airbus Passport Decom
iOS + Android · Airbus Passport decom · platform hardening. One MyIAM platform across Web + Mobile, with Passport functionality absorbed into the cockpit.
STATUS: Scope TBD · post-D3 decision · HO approval required before scheduling.
IAM Assistant chatbot
Agentic AI-assisted self-service chatbot for IAM queries. Not part of the current MyIAM Foundational Journey build.
STATUS: Out of scope for this programme. No build, design, or roadmap commitment as its part of new MFT
Restricted Standard Tech Stack
.Net , Angular & PowerShell is the current team tech stack. Claude Code expected Jul '26 as a future enabler for any shift.
STATUS: Out of scope ·Existing team skill is .net stack
⚠
Re-evaluation point - Above 2 items will be reassessed for future phases based on priority and capacity availability.
Airbus Amber
4
Availability of Claude Code by July’26
DRAFT

## Slide 4
MyIAM
Programme Roadmap
FY 2026
FY 2027
FY 2028
Q2
Apr–Jun
Q2
Jul–Sep
Q3
Oct–Dec
Q1
Jan–Mar
Q2
Apr–Jun
Q3
Jul–Sep
Q4
Oct–Dec
Q1
Jan–Mar
Q2
Apr–Jun
UI
Consolidation
Core Backend
& Integration
Module APIs
+ DevOps + IAM security principles
Decommissioning
UI (MFE) Consolidation
⬡ MFE Design
3 Apps Absorbed into MyAccess UI
✓ Cockpit Beta Release
· R1
✓ Go-Live R2
D1
Consolidation complete
MyIAM Full Build · Frontend + Backend Together
D4
✓ MFE Live · R6
Data Tier · Source X → MyIAM DB Sync (NiFi)
⬡ NiFi Design
NiFi Pipelines
AD→MyIAM Sync
Schema
Validation
✓ Foundation -1 · R3
Core API · Data Source X Write Ops · AD Write Authority
⬡ Core API Arch
Proto: Arch
+ Interface
D2
✓ Foundation -2
· R4
API Microservice · 4 MyX APIs modules migration
API microservice
Design
Password +
Account APIs
Group +
SSO APIs
D3
✓ API Live R5
· Infrastructure · DevSecOps · LPA, Zero Trust
Continues through project close →
↻ From 2029
Annual upgrade (Jul–Aug)
· MyX Apps Sunset
MyPassword
MyAppConnect
✓ Decom.
Complete
4 Apps
Retired
Go-live / release
G1–G4 decision gate
Prototype
MyIAM Evolvement
Transition gap
Phase boundary
Planning note
Core foundation complete
microservices complete
MyAccount
MyAccess
full build complete
⬡ Initial design microservice
IIDIA · Airbus India
Internal – v1.0 · Jun 2026
Buffer due to complex business →
DRAFT

## Slide 5
Parallel
Studies
Comparative analysis of application transition streams
PWM
IDFED to replace PWM in future
Under leadership of DIAA
Blockers solved
Once done, PWM will be decomm
MyAppConnect
Evaluation to start with Ping team on features
As-Is vs To-Be analysis to be performed
Post that a business case as needed will be performed
As a result, MyAppConnect is the last application to be scoped for decomm
Airbus Amber
10
DRAFT

## Slide 6
Call for
Action
Critical dependencies requiring HO decision
Capacity Escalation Path
The team is at capacity across all active phases. No mitigation exists today - if delivery is squeezed further, we need PM & HO backing to prioritize scope, not compress the roadmap.
ASK: Approve an escalation path: capacity issues go to reprioritization, not timeline compression.
DIAM - SelfService
AD Team Commitment
Phases 1 & 2 depend on continuous Active Directory support. This is an external dependency for infrastructure ,Accounts etc - it requires executive commitment, as MyIAM's source of truth is AD.
ASK: Confirm a dedicated AD liaison for MyIAM through Phases 1–2, with an early joint working session.
DIAC - IAM Core Services
⚠
Also flagged - MyIAM Mobile Platform + Airbus Passport Decom and IAM Copilot are currently out of scope; see Out of Scope slide for status and re-evaluation timing.
Airbus Amber
9
DRAFT

## Slide 7
Converged IAM PROGRAMME
Airbus Amber
Thank you!
Airbus Commercial · IIDIA