## Slide 1
ROADMAP
MyIAM · Beta Feb 2027 → Production Apr 2027
3
2026
2027
2028
Q2 2026 Apr–Jun
Q3 2026 Jul–Sep
Q4 2026 Oct–Dec
Q1 2027 Jan–Mar
Q2 2027 Apr–Jun
Q3 2027 Jul–Sep
Q4 2027 Oct–Dec
Q1 2028 Jan–Mar
Integration
Testing
Foundation
& Build
Data &
Integration
AD
Core
Decom-
mission
UI Consolidation
MFE shell · Front-end · UX POC Apr 2026
Testing
Front-end
✓ Solutions ✓ Context ✓ Groups ✓ Password ✓ Identity ✓ Accounts ○ MyAppConnect
◇ D1 UI foundation complete
○ UX POC · Apr 2026
API Development
Python APIs · started Aug 2026
Domain APIs · Solutions + Context + Groups
+ Password + Identity
✓ Solutions ✓ Context ✓ Groups ✓ Password ✓ Identity ○ Accounts ○ Connectors
◇ D2 API foundation complete
Data Sync (Prefect tool)
Config-over-code · Multi-source integration
AD → MyIAM DB ·
Multi-Source Sync
✓ AD Sync ✓ Pipeline Hosting ○ Additional Sources
◇ D3 Data sync complete
AD Write Consolidation
Sole write authority · Target release Feb 2027
Core API · AD Write Authority
○ Starts mid-Oct 2026: design → implementation → release by Feb 2027
◇ D4 AD write authority live
Decommissioning
MyPassword · MyAccount · MyAppConnect · MyAccess
MyX Apps Sunset
◇ D5 Decommissioning complete
MyPassword → MyAccount → MyAppConnect → MyAccess
Buffer – complex business
4 Apps Retired
⚑ BETA · Feb '27
⚑ PRODUCTION · Apr '27
Completion
Decision gate
⚑ Beta · Feb '27
⚑ Production · Apr '27
Integration Testing
⚠ Achieving key roadmap milestones including the Beta release and final Go-Live remains strictly dependent on the availability of the AI Assistant tool (Claude Code). Legacy app decommissioning begins post Go-Live and closes with buffer for business complexity.
DRAFT
AIRBUS