## Slide 1
MYIAM · TECH STACK EVOLUTION
.NET → Python Migration Playbook
A team-enablement roadmap for a six-developer, six-month backend rewrite
105K+
Confirmed LOC — Scope A APIs
6
Developers — .NET background
6 mo
Delivery window

## Slide 2
Six developers. Zero Python experience. Six months.
The constraint that decides whether this is achievable
105K+
Confirmed lines of code
Scope A: Core, MyAccount, MyAccess, MyPassword APIs — excludes Angular UI (→ React) and AppConnect (still open)
6
Developers assigned
All .NET background — none have production Python experience today
6 mo
Delivery window
≈ 780 developer-days total capacity across the team

## Slide 3
Capacity vs. scope — the real constraint
6 developers × ~130 working days, at realistic verified-output throughput for a team new to Python
Chart: 
| Capacity (low) | Capacity (high) | Scope A (APIs) | Scope B (everything)
Lines of code | 117000 | 312000 | 105000 | 400000
Scope A already sits close to low-end team capacity — before AppConnect's API is even added.

## Slide 4
01
Pilot on MyPassword First
Smallest, most isolated module (8,000 LOC) — the right instrument, not the easy deliverable
Run standalone with 2 developers — not in parallel with any other module
Deliverable 1: real throughput data, replacing assumptions with your team's actual LOC/day
Deliverable 2: a translation playbook — how exceptions, DI, and test structure map from C# to Python
Deliverable 3: a review checklist a .NET developer can run without needing Python fluency

## Slide 5
02
Turn the Pilot into a Go/No-Go Threshold
Target: ~135–155 verified LOC/developer/day — 105K LOC ÷ 780 developer-days, with almost no slack
Measure the pilot: verified LOC delivered ÷ developer-days spent by the 2 pilot developers
≥ 155 / day
Scale to full team as planned
110–155 / day
Proceed — flag timeline risk, recheck after next module
< 110 / day
Pause scaling — renegotiate scope or timeline now

## Slide 6
03
Sequence by Risk, Stagger the Team
Pair each pilot developer with 1–2 new joiners per module — transfers judgment, not just notes
Re-run the go/no-go math at every module boundary, not just once after the pilot
Reserve a part-time Python-fluent reviewer for Core API specifically — your highest concentration of risk
MyAccount
18,000 LOC
First — team still forming judgment
→
MyAccess
22,000 LOC
Second — confirm throughput holds
→
Core API
57,000 LOC
Last — highest complexity & integration

## Slide 7
04
Build an Automated Parity-Test Harness
Replace judgment-based review with characterization testing: same input → same output as the old .NET service = pass
Capture real request/response pairs per module; weight denial and error cases as heavily as the happy path
Make it the actual merge gate — not a manually-ticked checklist item
AI-suggested test inputs are fine; AI-predicted expected outputs are not — always validate against the live old system
Check for existing OpenAPI specs before hand-building contract-level tests

## Slide 8
05
Cut Over Module-by-Module with Shadow Traffic
Parallel run: old and new both process live traffic; only the old service serves users
Cut over read/check calls before write calls within each module
Keep instant rollback (flag or router switch) live for 2–4 weeks after each cutover
False grant
Python allows what .NET denies — security incident. Hard-blocks cutover, regardless of overall mismatch rate.
False deny
Python denies what .NET allows — a support ticket. Doesn't block cutover on its own.

## Slide 9
06
Decommission the Old Service, Per Module
Burn in at 100% Python traffic for 2–4 weeks before decommissioning starts — cutover confidence ≠ decommission confidence
Audit gateway/DNS logs for hidden dependents (batch jobs, reports, other services) before pulling anything down
Archive, don't delete — IAM data carries its own retention requirements
Close the loop: actual LOC/day vs. the ~135–155 target, actual spend vs. the token estimate, dual-run cost eliminated

## Slide 10
One Cycle, Repeated Per Module
Pilot lessons compound as the team scales into each larger module
1
Pilot
2
Threshold
3
Sequence
4
Verify
5
Cutover
6
Decommission
Each pass gets faster — the playbook, the harness, and the throughput data all carry forward.