# MyIAM Micro-Plan

Oct 8, 2026 · @Hameed

## Plan Overview

MyIAM micro-plan covers 5 delivery workstreams running in parallel from Oct 2026 through Feb 2027, with UX refinement as a continuous sixth track. All modules must reach dev-complete before the canary sequence begins in March 2027.

| Workstream | Start | Target Complete |
| --- | --- | --- |
| Data Collect (AD → MyIAM DB) | Oct 8 | End of October |
| Password Reset | Oct 8 | Beginning of November |
| Core API / AD Write Consolidation | Oct 8 | End of Nov / Dec first week |
| Solution & Context | Nov 1 | Mid-December |
| Groups | Mid-Nov | Mid-January |
| Accounts | Dec 1 | End of February |
| UX Refinement (all modules) | Oct 8 | Ongoing — parallel to all above |

## Sprint Plan

MyIAM workstreams · 7 parallel tracks · Oct 2026 to Feb 2027

### Sprint 1 — Oct 8 to Oct 21

Theme: Foundation sprint — all workstreams in motion

| Workstream | Scope this sprint | Owner |
| --- | --- | --- |
| Data Collect | Integrate remaining AD sources into Prefect pipeline; validate completeness | Data engineer |
| Password Reset | Add AD write call, policy validation, notification triggers | Team A Dev 1 + Team B backend |
| Core API / AD Write | Finalize architecture design; get sign-off from architect | Architect + Team B backend |
| Accounts API | Schema design + base API scaffolding | Team A Dev 2 |
| Solution & Context | Gap analysis against current API; begin hardening | Team A Dev 3 |
| UX Refinement | Begin refinement pass on Password Reset and Solution screens | UX |

Sprint exit criteria

- Password Reset business logic code-complete

- Accounts schema scaffolded

- Core API design signed off

- Data Collect on track for Oct 31 closure

### Sprint 2 — Oct 22 to Nov 4

Theme: Password Reset to done; Core API build begins

| Workstream | Scope this sprint | Owner |
| --- | --- | --- |
| Data Collect | Final source integrations; close and validate full AD read | Data engineer |
| Password Reset | Integration testing, defect fixes, sign-off | Team A Dev 1 + QA |
| Core API / AD Write | Sprint 1 of implementation — AD connection layer + shadow write setup | Team B backend + Architect |
| Accounts API | Business logic layer complete | Team A Dev 2 |
| Solution & Context | Integration testing; canary prep begins | Team A Dev 3 + Team B |
| UX Refinement | Groups and Accounts UX refinement pass | UX |

Sprint exit criteria

- ✅ Password Reset module dev-complete (first module done)

- ✅ Data Collect closed — all AD data in MyIAM DB

- Core API AD connection layer functional

- Accounts business logic complete

### Sprint 3 — Nov 5 to Nov 18

Theme: Core API mid-build; Solution & Context closes

| Workstream | Scope this sprint | Owner |
| --- | --- | --- |
| Core API / AD Write | Sprint 2 — dual-write shadow mode; internal write validation | Team B backend + Architect |
| Solution & Context | Final testing + sign-off | Team A Dev 3 + QA |
| Groups | API + schema build begins (most complex asset) | Team B backend |
| Accounts API | Integration testing; UX alignment | Team A Dev 2 |
| UX Refinement | Groups UX refinement pass | UX |

Sprint exit criteria

- ✅ Solution & Context module dev-complete

- Core API dual-write shadow validated internally

- Groups API underway

- Accounts integration testing in progress

### Sprint 4 — Nov 19 to Dec 2

Theme: Core API completion; Groups and Accounts in build

| Workstream | Scope this sprint | Owner |
| --- | --- | --- |
| Core API / AD Write | Final implementation — all asset write paths connected and tested | Team B backend + Architect |
| Groups | Business logic + write path integration | Team B backend |
| Accounts API | Final testing + sign-off prep | Team A Dev 2 + QA |
| UX Refinement | Accounts UX refinement pass | UX |

Sprint exit criteria

- ✅ Core API / AD Write Consolidation complete (all modules unblocked)

- Groups build 60% complete

- Accounts nearing sign-off

### Sprint 5 — Dec 3 to Dec 17

Theme: Groups closes; all prior modules production-ready

| Workstream | Scope this sprint | Owner |
| --- | --- | --- |
| Groups | Final testing + sign-off | Team B + QA |
| Accounts | Continued build + testing | Team A Dev 2 |
| All modules | Production readiness checklist per module; OpenShift hosting validation | DevOps + PO |
| UX Refinement | Final UX pass across all complete modules | UX |

Sprint exit criteria

- ✅ Groups module dev-complete

- All prior modules (Password Reset, Solution & Context, Core API) production-ready

- Accounts 50% complete

### Sprint 6 — Dec 18 to Jan 15

Theme: Accounts closes; platform stabilization

| Workstream | Scope this sprint | Owner |
| --- | --- | --- |
| Accounts | Final build, testing, and sign-off | Team A Dev 2 + QA |
| All modules | Platform-wide regression; performance validation | Team B + QA |
| UX Refinement | Close all outstanding UX items | UX |

Sprint exit criteria

- ✅ Accounts module dev-complete

- Full platform regression passed

- All 5 modules ready for canary sequence starting March 2027

## Milestone Summary

| # | Milestone | Target Date | Module |
| --- | --- | --- | --- |
| M1 | Data Collect complete — full AD read in MyIAM DB | End of October 2026 | Infrastructure |
| M2 | Password Reset — dev and testing complete | Beginning of November 2026 | Password Reset |
| M3 | Core API / AD Write Consolidation complete | End of November / Dec first week 2026 | All modules |
| M4 | Solution & Context — dev and testing complete | Mid-December 2026 | Solution & Context |
| M5 | Groups — dev and testing complete | Mid-January 2027 | Groups |
| M6 | Accounts — dev and testing complete | End of February 2027 | Accounts |
| M7 | Canary sequence begins | March 2027 | All modules |

Key dependency: M3 (Core API) is a prerequisite for all module canaries. All modules complete their own dev and testing independently, but none can go to canary until M3 is done.