## Slide 1
ROADMAP
MyIAM · Micro-Plan – Module Build Roadmap
Oct 2026 – Mar 2027 · 6 modules · 6 sprints · Core API = shared write layer gating all modules · ◆ = module complete
Oct '26
Nov '26
DST Gates
Dec'
26
Jan '27
Feb '27
Mar '27
S1
S2
S3
S4
S5
S6
1. Data Collect
Prefect pipeline · AD → MyIAM DB
already running → completes end Oct
◆ Pipeline Complete
✓ Module dev complete
2. Password Reset
Full biz logic incl. notifs
Runs parallel → replaces MyPassword
◆ DST Gate
◆ Module: Password
Reset Delivery
✓ Module dev complete
3. Core API / AD Write
Module-independent write layer
Unblocks all module canaries
◆ Core API
Complete
✓ Module dev complete
4. Solution & Context
App entitlements + context data
Runs parallel with Password Reset
◆ Component:
Data Sync
◆ Module: Solution
& Context
✓ Module dev complete
5. Groups
Group management
Start with 1 group → scale
◆ Module: Groups
✓ Module dev complete
6. Accounts
Account lifecycle
Starts once Core API complete
◆ Module: Accounts
✓ Module dev complete
▐ Core API Gate
UX Refinement — parallel across all sprints
Internal 1% (dark)
Pilot 10% → Ramp (light)
Pilot gate clear (triggers next module)
100% – module live
⚠ DST gates are a dependency · MyAppConnect is out of scope · If Canary doesn't succeed, we will fall back, replan and deliver