## Slide 1: MyIAM · High-Level Roadmap: Oct 2026 → Apr 2027
Gantt view: eight stages, each opening only when the one before it clears
2026
2027
Oct
Nov
Dec
Jan
Feb
Mar
Apr
BETA
GO-LIVE
ACCESS
1 · UX Prototype
Enabler · parallel build
Prototype
D1 · End Oct
2 · Data Sync
Enabler · multi-source
Multi-source sync
D2 · Mid Nov
3 · Core API
Enabler · AD write
Design → implementation
D3 · Mid Dec
4 · Integration & Testing
Verify · end-to-end
Integration
D4 · Mid Jan
5 · DST Review
Verify · single review
DST
Single review · clears mid Jan
6 · UAT
Accept · sign-off gate
UAT
D5 · Mid Feb
7 · Beta
Roll out · pilot users
Beta
Feb 2027 · pilot users
8 · Go-Live
Roll out · staged ramp
Go-Live ramp
Access live
Completion
D1–D5 decision gates
Beta · Feb 2027
Go-Live · Mar 2027
If any enabler slips (UX prototype, Data Sync, Core API) or Claude Code is delayed, integration, DST, UAT, Beta and Go-Live all move with it.
Notes: Gantt view of the eight stages. Enablers first: advanced UX prototype to end Oct, Data Sync to mid Nov, Core API (AD write authority) to mid Dec. Then integration and testing from mid Dec to mid Jan, with the single DST (Digital Security Review) cleared by mid Jan. UAT runs to mid Feb, Beta in Feb, Go-Live in Mar, and Access goes live in Apr after a ramp of at least three weeks. Bar start points and the DST window are indicative; confirm before presenting.

## Slide 2: MyIAM roadmap: enablers first, then five modules to go-live
Beta Feb 2027 · Go-live Mar 2027 · Access go-live Apr 2027 — if one enabler slips, every module moves with it
Q4 2026 · Oct–Dec
Jan 2027
Feb · BETA
Mar · GO-LIVE
Apr · ACCESS
ENABLERS
critical path
Claude Code availability
Core API · AD Write Authority
AD → DB Data Sync
Prerequisite block: all three in production by Dec 2026. No module canary starts until they clear.
Beta and Go-Live depend on Claude Code availability to deliver Core API and Data Sync on time.
GATES
DST · Digital Security Review (single approval)
Per-module quality gate: clean time window plus manual sign-off before each ramp step
Password Reset
Beta
Ramp → Live
Solution
Beta
Ramp → Live
Groups
Blocked until enablers and DST clear
Beta
Ramp → Live
Accounts
Beta
Ramp → Live
Access
Beta
Ramp ≥3 wks → Live
End-user comms
Same three messages repeat for every module
1 Announcement
2 Go-live notice
3 Post go-live feedback
IF ONE ENABLER SLIPS
Enabler late
DST waits
All module canaries move
Beta + Go-live move
Bar timing indicative · Status per module: Not released → Beta-Internal → Beta-Pilot → Live · MyAppConnect out of scope
Notes: Read left to right: enablers and the single DST review unblock every module. Each module then passes its own quality gate before ramping. Beta is February, go-live is March, and Access follows in April after a minimum three-week ramp. Hatched areas show where no module canary can start. If any enabler slips, the whole chain on the right moves. Bar positions are indicative; confirm exact dates per module.